## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-04-14 | Done | Magenta | I read about magenta and how to use it | Research | 4 | 4 | 0 | https://magenta.tensorflow.org/studio
| Done | Magenta | I read about magenta and how to use it | Research | 4 | 4 | 0 | https://magenta.tensorflow.org/aisongcontest
2025-04-15 | Done | Magenta | I read about magenta and how to use it | Research | 4 | 4 | 0 | https://magenta.tensorflow.org/music-transformer
| Done | Practice Notebooks | I found a couple of Notebooks which I decided to look | Programming | 4 | 4 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/tree/main/Practice_Notebooks
2025-04-16 | Done | Practice Notebooks | I found a couple of Notebooks which I decided to look | Programming | 4 | 4 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/tree/main/Practice_Notebooks
| Done | First model | I started writing my first magenta model | Programming | 4 | 4 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/blob/main/Deliverables/Magenta.ipynb
2025-04-17 | Done | First model | I finished, but unfortunately Magenta's library is not available | Programming | 8 | 8 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/blob/main/Deliverables/Magenta.ipynb | Uses magenta and I cant seem to install the library not in the server nor locally
2025-04-18 | Done | Suno | I read about Suno its API and how to use it | Research | 3 | 3 | 0 | https://dev.to/aws-builders/unlocking-musical-creativity-with-ai-generating-lyrics-and-melodies-55p0
| Done | Suno | I read about Suno its API and how to use it | Research | 1 | 1 | 0 | https://www.reddit.com/r/MachineLearning/comments/1d1vp2u/p_musicgpt_an_open_source_app_for_generating/
| Done | Suno | I read about Suno its API and how to use it | Research | 3 | 3 | 0 | https://github.com/Curated-Awesome-Lists/awesome-ai-music-generation
| Done | Suno | I read about Suno its API and how to use it | Research | 1 | 1 | 0 | https://soundful.com/how-to-guide-creating-music-with-ai-music-generators/
|  |  |  | Total Hours | 40 | 40 | 0
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2025-04-21 | Done | Suno model | I started writing my first Suno model | Programming | 8 | 8 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/blob/main/Deliverables/Suno%20API.ipynb
2025-04-22 | Done | Suno model | I kept writing my first Suno model | Programming | 8 | 8 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/blob/main/Deliverables/Suno%20API.ipynb
2025-04-23 | Done | Suno model | I finished, but unfortunately I couldn't figure out how to get sunos API | Programming | 2 | 3 | 1 | https://github.com/NoahIvanisevic235738/Music_generated_AI/blob/main/Deliverables/Suno%20API.ipynb | I can't figure out how to get Sunos API
| Done | Hugging face + Transformers | I read about a third option to make AI music | Research | 1 | 1 | 0 | https://www.youtube.com/watch?v=GQfKoIMpea8
| Done | Hugging face + Transformers | I read about a third option to make AI music | Research | 3 | 3 | 0 | https://github.com/gabotechs/MusicGPT
| Done | Hugging face + Transformers | I read about a third option to make AI music | Research | 2 | 2 | 0 | https://www.edlitera.com/blog/posts/musicgen
2025-04-24 | Done | Hugging face + Transformers | I read about a third option to make AI music | Research | 1 | 1 | 0 | https://www.edlitera.com/blog/posts/musicgen
| Done | Hugging face + Transformers | I read about a third option to make AI music | Research | 2 | 2 | 0 | https://mubert.com/
| Done | Hugging face + Transformers | I read about a third option to make AI music | Research | 5 | 5 | 0 | https://github.com/modal-labs/modal-examples/blob/main/06_gpu_and_ml/text-to-audio/musicgen.py
2025-04-25 | Done | Hugging face + Transformers model | I started coding the model hopefully it works this time | Programming | 6 | 6 | 0 | https://github.com/NoahIvanisevic235738/Music_generated_AI/blob/main/Deliverables/MusicGen%20(HuggingFace%20Transformers).ipynb
| Done | Working Log | I wrote down everything done | Evidencing | 2 | 2 | 0
|  |  |  | Total Hours | 40 | 41 | 1

## Overview (hidden)
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 0.3
Unplanned | Meeting | ILO 1.5
Blocked | Programming | ILO 2.5
In-Progress | Research | ILO 3.5
Done | Testing | ILO 4.4
Delayed | Workshop | ILO 7.3
Cancelled | Planning | ILO 11.2
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break